## Kick Off Go - No Go Template
Field View/Intelex Form Ref #
Owned by
Date
Status
Location
Supply Chain Partner / Work Pack details
Supply Chain Partner
Scope of Work
Contract Award Date
Kick-off Meeting Date
Site Commencement Date
LORA Package Owner Details
LORA Package Owner
Postion
Department
Supply Chain Partner Representative Details
Check Item | Representative Name | Email address | Mobile Phone Number
Project Manager
Project Supervisor
Health and Safety
Rail Safety
Environmental
SUPPLY CHAIN MOBILISATION REQUIREMENTS
Check Item |  | Response | Reference Number | Approval Overide (Construction or Project Manager)
Project Risk Assessment meeting record completed (Field View Form ­where applicable)
Intelex – FSR assessment tool (System only) has been completed for all FSR’s?
Intelex – SER assessment tool (System only) has been completed for all SER’s?
Approved SWMS Part A & B relevant to work package has been completed.
HSEMS System Requirements – 12­week post mobilisation audit scheduled in Intelex and assigned to Project HSE Lead.
HSEMS System Requirements – 6­month post mobilisation audit scheduled in Intelex and assigned to Project HSE Lead.
Heavy Vehicle Self Assessment has been completed.
HSE SYSTEM - POST MOBILISATION REQUIREMENTS
Check item |  | Response | Intelex Reference Number | Approval Overide (Construction or Project Manager)
Intelex – FSR assessment tool (Field) completed for all applicable FSR’s with relevant area Supervisor* (Field element to be completed after mobilisatiion commenced).
Intelex – SWMS Observation tool (Part C) completed for package works with relevant area Supervisor.
Intelex – SER assessment tool (Field) completed for all applicable SER’s with relevant area Supervisor* (Field element to be completed after mobilisation commenced).
FATAL + SEVERE RISK (FSR)
Check item | Select if applicable to scope | GO / NO GO | Intelex Reference Number
FSR Asbestos
FSR Chain of Responsibility
FSR Confined Space
FSR Cranes + Lifting
FSR Demolition
FSR Excavation
FSR Formwork + Falsework
FSR General Electrical Safety
FSR Plant + Equipment
FSR Plant + Equipment Isolations + Lockouts
FSR Piling
FSR Precast + Tilt Up Concrete
FSR Rail Operations
FSR Scaffolding
FSR Traffic Management
FSR Utilities + Services
FSR Work On, Over or Adjacent to Water
FSR Working at Heights
MOBILISATION
Check item |  |  | GO / NO GO
Supply Chain Partner informed of the Datascope (or other) mobilisation process and estimated timeframes?
TRAINING & COMPETENCY
Check item |  |  | GO / NO GO
Supply Chain Partner agrees all High­risk work activities will be undertaken by trained personnel only?
Supply Chain Partner agrees to utilise the LOR Datascope system (or other) to record and manage training records?
Supply Chain Partner informed of the Datascope (or other) job role requirements when uploading into Datascope system?
Supply Chain Partner informed of the VOC requirements. (i.e. make & model specific / within 2 yrs)?
PLANT & EQUIPMENT
Check item |  |  | GO / NO GO
Supply Chain Partner has been informed of the Plant and Equipment mobilisation requirements?
Supply Chain Partner informed of the project Plant ID sticker requirements?
PROJECT INDUCTION & RETHINKING ENGAGEMENT WORKSHOP
Check item |  |  | GO / NO GO
Supply Chain Partner has been informed of Induction requirements?
Supply Chain Partner informed of Project Induction/Engagement workshop days/ timeframes?
FITNESS FOR WORK
Check item |  |  | GO / NO GO
Supply Chain Partner informed a BAC level of 0.00% applies to all LOR project sites?
Supply Chain Partner informed of project requirements to declare prescription medication?
Supply Chain Partner informed of project D&A testing requirements and processes?
EVENT NOTIFICATION
Check item |  |  | GO / NO GO
Supply Chain Partner informed of the project requirement to report incident immediately?
Supply Chain Partner informed of project injury notification and management processes?
Supply Chain Partner informed of the required project timeframes for incident investigation and closeout?
PPE REQUIREMENTS
Check item |  |  | GO / NO GO
Supply Chain Partner informed of the project PPE requirements ?
Task specific PPE identified and supply chain partner have been informed.
MOBILE PHONE & SOCIAL MEDIA
Check item |  |  | GO / NO GO
Supply Chain Partner informed of project mobile phone use and social media policies?
GOVERNANCE TOOLS
Check item |  |  | GO / NO GO
Supply Chain Partner informed of Assurance Activity tools?
SUPERVISION REQUIREMENTS
Check item |  |  | GO / NO GO
Supply Chain Partner agrees to provide full­time competent supervision for their work package?
Supply Chain Partner agrees to provide adequate Supervision levels based on work scope risk profile?
CHAIN OF RESPONSIBILITY
Check item |  |  | GO / NO GO
Supply Chain Partner agrees to manage the Chain of Responsibility in line with Laing O'Rourke requirements.
Supply Chain Partner has been informed of the requirement to complete the Heavy Vehicle National Legislation Self Assessment (if applicable).
RAIL REQUIREMENTS - IF APPLICABLE
Check item |  |  | GO / NO GO
Supply Chain Partner informed of project rail specific training requirements applicable to work scope?
Supply Chain Partner has been informed of requirement to complete a Rail Specific PRA (if applicable).
PROJECT RISK ASSESSMENT (PRA)
Check item |  |  | GO / NO GO
Supply Chain Partner informed of requirement to provide PRA for scope of work?
SAFE WORK METHOD STATEMENTS (SWMS)
Check item |  |  | GO / NO GO
Supply Chain Partner informed of the requirementa SWMS must meet as per SR SWMS Section 2.1 Part A SWMS Development?
Supply Chain Partner informed of requirement for SWMS to be submitted for review & acceptance prior to commencing work and the review timeframes?
PROJECT HSE AUDIT REQUIREMENTS
Check item |  |  | GO / NO GO
Supply Chain Partner informed of 12 week post mobilisation audit requirement?
Supply Chain Partner informed of 6 month post mobilisation requirement?
HSEMS DOCUMENT LIBRARY
Check item |  |  | GO / NO GO
Supply Chain Partner has been informed of the LOR HSEMS Online System and document library?
ENVIRONMENTAL REQUIREMENTS
Check item |  |  | GO / NO GO
Supply Chain Partner has been informed of the project Construction Environmental Management Plan (CEMP) & made aware of the environmental requirements and details.
Supply Chain Partner has been informed of the Projects State and Commonwealth legislative Environmental Conditions for the area they are working (if/where applicable).
Supply Chain Partner has been informed of the Projects Environmental Control Assessment Maps (ECAM) detailing the environmental requirements and controls to specific work areas within the project.
Supply Chain Partner has been informed of any sensitive environmental requirements within their area of works.
Supply Chain Partner has been informed that any chemicals brought to site need to be declared on a hazmat register with chemical appropriate SDS (in date) prior to coming onto site.
SUPPLY CHAIN REPORTING REQUIREMENTS
Check item |  |  | GO / NO GO
Supply Chain Partner has been informed of the monthly reporting requirements to the project which covers data applicable as part of the contractual reporting.
SEVERE ENVIRONMENTAL RISK (SER)
Check item | Select if applicable to scope | GO / NO GO | Field View Reference Number
SER Air Quality and Dust
SER Biodiversity
SER Biosecurity
SER Cultural and European Heritage
SER Contamination Management
SER Dangerous Goods + Chemical Management
SER Erosion and Sediment Control
SER Groundwater Dewatering
SER Groundwater Management
SER Noise and Vibration
SER Spoil and Waste Management
SER Surface Water Management
SER Temporary Waterway Structures

## Data (hidden)
Go/No Go | Yes
GO | No
NO GO | N/A