## FSR03
SITE / LOCATION:
OBSERVERS: |  |  |  |  | DATE:
SCOPE: |  | To eliminate or minimise the risks of fatalities, injuries and events arising from the use of cranes and lifting operations.
Control Type | Control Number | Check Type | Control Description | Criteria | Compliance (Y / N) | Comments
CRITICAL | 1 | S | PLANNING An Crane Appointed Person is in place | Letter of Appointment in place which outlines Appointed Persons roles and responsibilities |  | Project to document name of Appointed Person
|  |  |  | Deputy Crane Appointed Person is appointed and suitably qualified |  | Project to document name of Deputy Appointed Person
Crane Appointed Person has approved the Lifting Operation Plan
Crane Appointed Person holds relevant competencies - Crane Supervisor & Appointed Person (Lifting Operations - CTI Course) or; - NPORS (National Plant Operators Registration Scheme) or: - Equivalent Qualification Verified by LORAC.
CRITICAL | 2 | S | PLANNING A Crane Supervisor is appointed | Letter of Appointment in place which outlines Crane Supervisor roles and responsibilities |  | Project to document name(s) of Crane Supervisor
Evidence that the Crane Appointed Person is monitoring/checking Crane Supervisor responsibilities in the field
The Crane Supervisor must be a Competent Person in respect to crane operations, and hold one of the following qualifications; 1. A National License To Perform High Risk Work for crane operation Class C6 or above, or 2. A Crane Supervisor qualification issued by Crane Supervisor & Appointed Person (Lifting Operations - CTI Course); or NPORS (National Plant Operators Registration Scheme) or equivalent qualification verified by Laing O’Rourke, or 3. A National License To Perform High Risk Work Class Intermediate Rigging (RI) or above
CRITICAL | 3 | S | PLANNING A Crane "Lift Study" in place | Crane "Lift Study" is approved and implemented for all lifts that fall into the below criteria but not limited to: |  | Reference Lifting Categories and Associated Approvals Guidelines
|  |  |  | 1. Lifts over public roads and highways (all risks that could impact major infrastructure must have appropriate controls in place including emergency response and contingency plans - post consultation with relevant authorities) 2. Cranes operating with specialist rigging enhancements such as Superlifts 3. Pick and Carry Operations by Cranes (including Pick and Carry operations undertaken by Telehandler or Excavator) |  | Note: refer to "Lifting Categories & Associate Approvals Guidelines" when reviewing this section:
Has the "Lift Study" been communicated with crane team and adjacent work crews
There is a schedule of common lifts in place for Project Standard / frequently lifted materials / equipment and it's included in the Lifting Operations Plan and communicated to Crane Teams and ajacent work crews.
CRITICAL | 4 | S | A "Critical Lift Plan" is in place | Crane "Critical Lift Plan" is approved and implemented for all lifts that fall into the below criteria but not limited to: |  | Reference Lifting Categories and Associated Approvals Guidelines
|  |  |  | 1. "Non Simple" Multiple Crane Lifts (2 or more cranes) 2. Lifts involving persons suspended in Workbox - must also meet all the criteria of the Workbox permit 3. Lifts associated with demolition rigging 4. Cranes and mobile plant being used as a crane, working over 90% of maximum rated capacity (not including tower cranes 5. Lifting from on or off barges 6. Lifts involving submerged objects 7. Dual Winch Lifting |  | Note: refer to "Lifting Categories & Associated Approvals Guidelines" when reviewing this section:
Has the "Critical Lift Plan" been communicated with crane team and adjacent work crews
CRITICAL | 5 | S | PLANNING Temporary works, stability and ground bearing pressure for crane pads are verified for crane use (including suspended slabs /floors) | Requirement for suitable crane pad is included in the Temporary Works Control Register
Crane pad has been constructed as per design and verified (as per Temporary Works Control Register)
Temporary works potentially impacted by crane operations is protected and managed via the temporary works system i.e. scaffold, formwork, pre-cast. Control for FSR 17 U&S has been implemented as required.
Engineering report and survey data available for loading on suspended slabs and TW design is in place if slabs require to be backpropoped supported
Written report (Permit to load) generated for Appointed Person and is reviewed prior to set-up
CRITICAL | 6 | S | PLANNING Coordination arrangements are in place to effectively manage multiple crane operations. | Lifting activities and logistics (incl. Set-up and demobilisation) are discussed and coordinated via daily briefings and weekly meeting.
CRITICAL | 7 | S | EQUIPMENT Cranes and lifting equipment inspected and certified before mobilisation and use | Tower Crane Report is on the Temporary Works Control Register
Tower Crane Pre-Erection Inspection Report issued
A commissioning report is in place for tower cranes
Plant Item Registration issued by relevant Regulatory Authority
Lifting equipment register and test certificates are available
Where Non Destructive Testing (NDT) is required it is conducted by NATA Accredited Tester
|  |  |  | Inspections conducted by competent personnel (Pre-Erection and commission of tower cranes, lifting equipment inspection and crane pre-start) and regular TW inspections of tower crane base / crane base connections being carried out weekly |  | Project to define competency requirements (i.e. educational or vocational qualifications in an engineering discipline relevant to the plant, or knowledge of the technical standards relevant to the plant to be inspected)
CRITICAL | 8 | S | EQUIPMENT Soft slings are not in use | Where the use of soft slings is required relevant approvals obtained (from senior business leader/project director) and a permit system implemented for use. |  | No soft slings in use
CRITICAL | 9 | S | PEOPLE Personnel involved in lifting operations are trained and competent | Records of Operator VOC's conducted and within date (Theory and Practical Assessment Completed) |  | Project to determine what they accept as VOC
VOCs conducted by suitable qualified person at a frequency of every 2 years (Cert IV Training and Subject Matter Expert holding relevant ticket / licence) or Registered Training Organisation
|  |  |  | High Risk Licences available and reviewed as part of VOC process |  | Project to define high risk licences required for crane operations
CRITICAL | 10 | F | PLANNING Lifting operations are effectively planned and managed. | Lifting Operations Plan is in place and includes schedule of common lifts in place
Positive communications in place (as per Lifting Operations Plan or SWMS)
Backup communications in place (as per Lifting Operations Plan or SWMS)
Crane Lift Study Plan in place Refer to definition at Critical Control # 3
Crane Supervisor assigned and available to monitor lifting operations.
Operational Pre-start completed
Barricading and exclusion zones in place
Clearance from overhead services and obstructions is effectively managed
Free-fall functionality is deactivated. If free-fall isolation is not practicable a physical lock prevents inadvertent engagement. NOTE: Form Mobile Crane Pre-Mobilisation Checklist is completed and assesses for Free- Fall Functionality.
Ground condition checked daily designated person as per the Lift Analysis Plan
Crane outrigger settings are in accordance with the load chart being used and are in line with manufacturer’s operating instructions for the specific type of mobile crane
Outriggers are positioned on outrigger pads/timber as per the Lift Analysis Plan (OEM and load chart in use)
Adverse weather conditions are monitored
Crane Supervisor has reviewed crane set-up prior to lifting operations commencing (related to high risk lifts)
Simultaneous operations (SIMOPS) to also be communicated at Pre-Start/task briefing and also referenced within task SWMS
CRITICAL | 11 | F | PLANNING Plant is operated in a safe manner | OEM requirements are understood by operators , in place and followed
|  |  |  | Vehicle Management Plan is in place for pick and carry operations |  | Required when traveling on Public or on site internal haul roads
Rules are established & enacted for plant following plant or overtaking manoeuvres - safe separation is evident and maintained - communication and signage in place as appropriate
Evidence of review of pick and carry operations onsite by the Crane Appointed Person
All plant using a jib attachment for lifting operations have manufacturer supplied and or compatible attachments and load charts. (Must be equal to or exceeds lifting capacity of planned lift)
All Tele-handlers using jib attachments for lifting operations have a Calibrated Load Management Indicator systems.
Selection and use of plant for pick and carry is assessed and approved by the Crane appointed person
Articulated Mobile Cranes (Frannas) are not in use
CRITICAL | 12 | F | EQUIPMENT Lifting gear is certified and fit for use | Tagging or marking of lifting gear, with suitable current colour-coded tag or marker.
Defective or un-tagged equipment is immediately removed from service (effectively tag out)
Lifting gear in use is as listed in the relevant Lift Documentation / Plans.
Lifting gear not in use to be stored free from the elements.
CRITICAL | 13 | F | EQUIPMENT A tower crane anti-collision system is operational where there is radius overlap | Anti-collision system fitted and used in all tower cranes.
|  |  |  | Anti-collision system (if required to be locked out or disabled) must be authorised by Crane Appointed Person and associated Risk Assessment completed. Must also be carried out by a trained competent operator. |  | Note: there is a physical key, only controlled a trained competent operator of the system (must be covered in VOC or familiarisation)
SWMS & Toolbox talk reflects lockout of anti-collision system and alternative controls in place to manage risk and/or collision with other plant
Dedicated zoning systems in place and monitored. AP to have approved zoning of Tower Cranes
STANDARD | 14 | F | EQUIPMENT Earthmoving equipment is used as a crane only under the following conditions (as per criteria) | Plant assessed and approved for lifting operations (load charts, SWL on dipper arm, hose burst valves, closed rated lifting points, level indicators and rated by OEM to operate as lifting device)
No high risk lifting
All loads must be slung by a competent person (RB, DG)
Dogman or Riggers in place with effective communication if the operator is unable to see the load at all times.
Operator has a VOC for the excavator when configured for crane operation.
This FSR review has been undertaken in line with the requirements and with evidence reviewed to ensure criteria has been adequately assessed and confirm results are reflective of what has been found:
Signed Review Members: |  |  |  |  | Date:
FATAL AND SEVERE RISKS - CONTROL ADEQUACY ASSESSMENT TOOL PERFORMANCE STANDARD - CRANES AND LIFTING

## Compliance (hidden)
N/A
Y
N